## lead
Project Name: E-Medicare
Group Number - 1
Team Lead - V.Harihara Krishna
Backend Lead - Rose Mary
Frontend Lead - Sabira

## activity tracker
slno | Employee ID | Name | Domain | Module | 21st OCT | 22nd OCT | 23rd Oct | 24th Oct | 25th Oct | 26th oct | 27th Oct
1 | 2528724 | Riyana Saffrin M | BACKEND & FRONTEND | registeruser | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING | FINAL PROJECT MEET
2 | 2530401 | Mirudula Ravichandran | BACKEND & FRONTEND | updatepassword | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
3 | 2528971 | Priyadharshini X | BACKEND & FRONTEND | add update and delete item | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
4 | 2528448 | Rose Mary Varghese | BACKEND & FRONTEND | Login/userlogin | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
5 | 2528996 | Sabira Nazar | BACKEND & FRONTEND | Cart | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
6 | 2528831 | Logesh X | BACKEND & FRONTEND | search by price | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
7 | 2529663 | J Rajeshwaran | BACKEND & FRONTEND | Payment and Contact Us | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
8 | 2529550 | V Harihara Krishna | BACKEND & FRONTEND | Search Filter | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
9 | 2530624 | Sarthak Agarwal | BACKEND & FRONTEND | Searchbar backend | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING
10 | 2528607 | Mathivathani B | BACKEND & FRONTEND | Order summary page & purchase | DB created along with Module completion |  | FRONTEND INITIATION | FRONTEND HTML CSS COMPLETION | FRONTEND BACKEND LINKING | JUNIT TESTING

## daily sprint
Meeting Date | Time | Progress Check | Time | Problem Solving
2022-10-21 | 10:00 | a | 4:45 | a
2022-10-22 | 12:00 | a | 16:00 | a
2022-10-23 | 11:45 | a | 16:00 | a
2022-10-24 | 11:30 | a | 18:00 | a
2022-10-25 | 13:00 | a | 16:30 | a
2022-10-26 | 9:30 | a | 5:30 | a
2022-10-27 | 9:30 | a